# TECHNICAL REPORT (PART B)

PROJECT
Project number:	[101094872]
Project name:	[A 360 DEGREES PERSPECTIVE ON THE VALUE OF MUSIC]
Project acronym:	[Music360]

REPORTING PERIOD / Please note that you must report on the entire reporting period.
RP number:	[1]
Duration:	from [01/03/2024] to [28/02/2026] M13 – M36

#@PER-REP-HE@#
#@PRO-GRE-PG@# [This document is tagged. Do not delete the tags; they are needed for the processing.]
## 1. Explanation of the work carried out and Overview of the progress
 The Music360 project set out to meet three challenges in the European music industry:
- (C1) Distribution fairness. Improve the fairness of the distribution of author and neighboring rights by basing it on the actual use of music;
- (C2) Fair compensation. Develop a method to measure the value of music, that can be used to motivate fair compensation for the use of music;
- (C3) Transparency. Make the information about actual use of music, and of its value available to stakeholders and decision makers, respecting confidentiality requirements

To meet these challenges, we formulated five goals, each of which has been achieved in a work package.

1. We defined a conceptual framework that defines the monetary and non-monetary value of music and defines ways to measure it. This contributes to fair compensation.
2. We defined a decentralized data architecture to collect data from CMOs that preserves ownership of the data by CMOs. This contributes to distribution fairness.
3. We implemented the Music360 platform to collect data and present its value to stakeholders and decision makers, preserving confidentiality. This contributes to transparency.
4. We developed a business model for the platform that demonstrates its viability in the long run. This contributes to the uptake of our solution after the project is finished.
5. We validated the definition of value, the measurement method, the decentralized architecture, and the platform by means of living labs in several European countries, performed by the CMOs in the project. The business model was validated by collecting feedback from musicians, CMOs, the worldwide associations of CMOs, SCAPR and CISAC, and EU policymakers.

### 1.1 Objectives
Objective 1: Conceptualization and measurement of the monetary and non-monetary value of music / This objective has been achieved. The results are documented in deliverable D1.2 (A framework to quantify and qualify the value of music – version 2). / Objective 2: Standardized, trusted, and unified collection and representation of music metadata. / This objective has been partly achieved. The results are documented in three deliverables: / D2.4: An ontology of the value of music – version 2 / D2.5: A distributed architecture and implementation for music data collection, representation, and distribution -version 2 / D2.6: Secure and trusted sharing of music data – version 2. / D2.4 and D2.5 are the finished results validated by our living lab experiments. D2.6 defines a first version of a trusted architecture, but it needs more work because current scientific results in secure multi-party computing have proven to be further from practice than we expected at the outset of the project. / Objective 3: Stakeholder-level reporting and analysis of the value of music. / This objective has been achieved, and the results are documented in D3.2 (Reusable dashboards to present and analyze the value of music – version 2), which was validated in the living labs and focus group sessions with musicians and policy makers. The dashboard requires users to log in using the author identifier (IPI) and/or performer identifier (IPN) known by their CMO. This allows relating author and performer identifiers as well as relating the international standard codes for works (ISWC) and recordings (ISRC). This has not been achieved by any other system yet and is an important contribution to the music sector. / Objective 4: Ecosystem-level reporting and analysis of music value creation, distribution, and consumption. / This objective was partially achieved and documented in D4.2 (Dashboard for ecosystem level value analysis -version 2). Reporting to policy makers, journalists, researchers etc. requires aggregate data about the entire ecosystem that preserves anonymity. We created a dashboard that shows the structure of the music ecosystem and how each party in it creates and consumes value. Our intention was to fully automate the aggregation of data collected from CMOs, but this proved too ambitious because there is no uniform algorithm to transform the available data into the form needed for the dashboard. In our dashboard demonstration, we therefore performed this transformation ourselves. Our results show that ecosystem-level reporting on value flows is an important decision-support tool for policymakers. / Objective 5: Sustainable business model of the Music360 dashboard. / This objective has been achieved, and the results are documented in D5.2 (Sustainable business model of Music360 dashboard – version 2). The business model of the Music360 dashboard is an extension of the ecosystem model developed for Objective 4, incorporating the dashboard and indicating how it creates and receives value. We additionally defined a possible governance structure for the dashboard. The dashboard has been validated by collecting feedback from musicians, the CMOs, from the worldwide associations of CMOs SCAPR and CISAC, and from EU policymakers. / Each of these objects has been worked on by a work package. In addition, Work package 6 performed experiments in living labs in the Netherlands, Ireland, Finland, Spain, and Portugal. These were performed as intended. / Finally, Work packages 7, 8, and 9 dealt with dissemination, project management, and ethics.

### 1.2 Explanation of the work carried out per WP
	Objective 1: Conceptualization and measurement of the monetary and non-monetary value of music	Objective 2: Standardized, trusted, and unified collection and representation of music metadata.	Objective 3: Stakeholder-level reporting and analysis of the value of music.	Objective 4: Ecosystem-level reporting and analysis of music value creation, distribution and consumption	Objective 5: Sustainable business model of the Music360 dashboard.
WP1: Conceptualization and measurement of monetary and non-monetary value of music	x
WP2: Standardized, trusted and unified collection of music metadata		x
WP3: Stakeholder-level reporting and analysis of the value of music			x
WP4: Ecosystem-level reporting and analysis of music value creation, distribution and consumption				x
WP5: Sustainable business model of Music360 solution					x
WP6: Living labs	x	x	x	x	x

    1. Work Package 1- Conceptualization and measurement of monetary and non-monetary value of music:
The aim of Music360 is to capture the full spectrum of values associated with background music, both economic and non-economic. Teams from the VU and UPV both developed a framework for music value, with UPV focusing more on the non-economic, qualitative aspects of value and the VU on the economic value of music in a business setting. The integration of both frameworks constituted the foundation for the ontology developed in WP2 and for the subsequent configuration of the dashboard. / WP1 identified, defined, and measured relevant value dimensions of background music to provide information on stakeholders involved in value creation, the types of venues to be selected for experimentation, and the specific value outcomes that were studied. This work was developed in close coordination with WP6, ensuring regular information exchange and alignment across the project. / Consortium meetings were central to consolidating and refining this work: / Valencia, September 2023: initial discussions defined the set of value dimensions to be included in the model and clarified the relationships between variables and expected outcomes. / UPV, April 2024: dedicated sessions on the living labs and on the value‑analysis dashboard helped align conceptual development, data requirements and technical specifications. / Dublin, September 2024: the consortium reviewed the status of the living labs, discussed lessons learned for the second round, and conducted a specific workshop on Deliverable D1.2. / Finland, April 2025: partners worked on integrating social and health value dimensions into the dashboard and reviewed the expected outputs for each living lab. / Lisbon, September 2025: the consortium revisited the progress and results of the living labs in the context of D6.6 and prepared contributions for the final reporting. / This iterative and collaborative process ensured strong coherence between the conceptualization in WP1, the living lab research carried out in WP6 and the technical requirements transferred to the platform, reinforcing the internal consistency of the project. / Description of work progress / As a result of WP1, a comprehensive framework for quantifying and qualifying the value of music has been established. The development process followed an iterative three‑step approach: 1) a systematic review of previous studies on the value of background music; 2) the adaptation of different value‑assessment models to the specific contexts of the living labs; and 3) a refinement of the framework based on the empirical data collected during these studies. / This process enabled Music360 to integrate validated value dimensions into the platform, providing empirical evidence on how background music generates value for different stakeholders. / The progress achieved in WP1 resulted from continuous coordination across the project. Feedback obtained during the Valencia meeting in September 2023 played a key role in refining the conceptual model and clarifying the links between values, stakeholders and expected outputs. Subsequent consortium meetings further aligned WP1 with the design and implementation of the living labs, the definition of measurement strategies, and the technical and analytical requirements of the Music360 dashboard. / Tasks / T1.1a/b Modelling the value of music (Q1.1, Q1.3). / T1.1a/b focused on developing a conceptual model of the monetary and non‑monetary value of music, addressing Q1.1 (identification of value components) and Q1.3 (relationships among value dimensions and implications for measurement). The work followed a structured, collaborative approach that involved all WP1 partners. / The task began with an academic literature review covering the economic, emotional, social, cultural, and health-related values of music. This review was jointly conducted by VU (economic and monetary perspectives) and UPV (non‑economic value dimensions). The analysis revealed that prior literature is well developed for economic value—particularly indirect effects—and for individual/private values such as emotional responses and therapeutic benefits. In contrast, shared and public values (cultural, social, and ethical) are significantly less studied, indicating the need for a broader integrative framework. / Based on this review, partners collaboratively developed a multi-perspective conceptual framework integrating the different forms of value and linking them to the contexts in which background music is used. VU, GTM, and UPV contributed to identifying value mechanisms affecting customers, IMRO focused on employee-related value dimensions, and UPV provided input regarding patient‑oriented and well‑being dimensions. TVE contributed insights on venue typologies—retail, hospitality, festivities, health, and others—and how value creation varies across these environments. / This framework also incorporated the perspectives needed to prepare the living labs. BMAT contributed with expertise on music data, metadata structures, and technical constraints relevant for subsequent measurement in WP2 and WP6, ensuring the feasibility of operationalization. GTM, IMRO, TVE, BMAT, UPV, and VU jointly discussed and validated the proposed value dimensions and their interrelations during project workshops (WS2 and WS5), both held with physical attendance. These collaborative sessions enabled each partner to contribute domain‑specific insights and refine the conceptual architecture. / Overall, T1.1a/b produced a validated conceptual model that defines: a) the key monetary and non‑monetary value components of music (Q1.1), b) the stakeholders and venues in which these values emerge, and c) the hypothesized relationships among value drivers, emotional responses, and measurable outcomes (Q1.3), forming the basis for subsequent field studies and experimental interventions. / This multi-stakeholder, multi-context model provides the conceptual foundation for measurement strategies in WP1, the ontology in WP2, and the experimental design of the living labs in WP6. / T1.2a/b Measuring value of music (Q1.2). / In this task, carried out in close coordination with WP6 and the design of the living labs, the objective was to determine how the different value dimensions of music can be measured by stakeholder type and venue characteristics (VU, GTM, UPV, BMAT). To guide this work, we developed a matrix that distinguishes between indoor and outdoor venues, economic and non‑economic value dimensions, and the specific use of background music (as opposed to foreground music). This matrix served as a foundational tool for selecting appropriate measurement approaches and identifying priority areas for data collection. / In parallel, the music ecosystem (TVE, UPV) was analyzed to map stakeholders, clarify how value is created and transferred, and identify relevant research questions for each living lab. Based on these questions, methodologies were adapted to the objectives and context of each lab. Quantitative methods were selected for economic value dimensions and for non‑economic values with measurable economic spill‑overs (VU, GTM, IMRO). For non‑economic value dimensions (UPV)—far less studied and requiring deeper exploration—we adopted qualitative or quantitative methods depending on the objectives and venues. / Measuring non‑economic values posed several specific challenges. For example, assessing the therapeutic value of music required identifying an appropriate scale to capture patients' benefits. In the living lab involving cancer patients, background music was found to improve anxiety, relaxation, pain, fatigue, and other symptoms associated with cancer. To capture cultural and social value in popular festivities and community‑based events, UPV adapted selected items from validated measurement models identified during the literature review. Ethical value was addressed primarily through qualitative approaches, focusing on the transmission of positive values through music and on the event's broader social meaning. / Workshops WS2 and WS5 provided an important space to align on the preparation of the living labs. Partners shared methodological considerations, discussed how to collect data effectively (with technical support from BMAT), and adjusted measurement strategies according to stakeholder profiles and the specific value dimensions to be analyzed. / T1.3a/b Analyzing value of music (Q1.4). / The previous tasks enabled us not only to analyze the data collected in the living labs but also to refine the conceptual framework itself, generating new insights, for example, regarding ethical value (UPV) or the impact of non‑copyrighted music (GTM). The analysis of the living labs identified new playlist features (BMAT, UPV), evidence of stronger impacts on employees (IMRO, VU), and comparative findings on the effects of live versus recorded music in patient contexts (UPV). Results obtained from the two music‑therapy tools demonstrated that different musical approaches yield distinct therapeutic benefits, providing evidence to support the personalization of background music to enhance its therapeutic value. / Additional living lab results (Netherlands, Finland) contributed to understanding how background music can improve servicescapes, benefiting both employees and customers (Finland, Netherlands), or enhance the overall user experience (UPV). Findings from a study in Spain also highlighted the relationships among cultural, social, and emotional values. In another study in Spain, ethical value was examined in depth, focusing on how music contributes to the transmission of positive social meanings and values. / The joint presentation and discussion of national studies during the workshops generated valuable synergies, supporting a broader assessment of the measures employed by different venues and the value dimensions perceived by various stakeholders. These exchanges also facilitated the integration of study data into both the dashboard and the CMO model, strengthening the alignment between empirical findings, conceptual reasoning, and platform requirements. / Deliverables / D1.1: A framework to quantify and qualify the value of music – version 1 (month 5). / D1.1, led by UPV with contributions from VU and TVE, established the initial framework for conceptualizing the different dimensions of value associated with background music. The deliverable identified how these value dimensions vary across venues and stakeholders and provided a structured approach to distinguish and describe these differences. / Once the variability and multidimensional nature of value were recognized, the team examined how each value dimension could be operationalized—translating conceptual definitions into measurable variables and indicators. This first version of the framework, therefore, represented an essential starting point, enabling the identification of key concepts to be measured as well as the methods and tools suitable for doing so. / D1.1 served as the foundation for the design and implementation of the first round of living labs (UPV, VU, GTM, IMRO). The insights generated in this deliverable also informed the initial specification of the data requirements for the Music360 dashboard (UPV, VU, BMAT), ensuring coherence between conceptual development, empirical testing, and platform needs. / D1.2: A framework to quantify and qualify the value of music – version 2 (UPV)(month 10) (R2/R3/R4) / D1.2, led by UPV, refined and expanded the initial framework based on the first results obtained from the living labs. This second version integrated the insights generated during the early implementation phase and identified additional information required for the second round of living labs (VU, UPV, GTM, IMRO, BMAT). / The evaluation of the framework enabled the inclusion of new value dimensions—such as ethical value—and supported a more systematic comparison of stakeholder groups (e.g., customers vs. employees). These comparisons helped identify patterns of congruence and shared values across different users of background music, improving the robustness and applicability of the model. / Overall, D1.2 strengthened the conceptual foundations of the project by ensuring that the framework evolved in response to empirical evidence, thereby improving its relevance for subsequent measurement activities and for the integration of data into the Music360 dashboard.

#### 1.2.2 Work Package 2 - Standardized, trusted and unified collection of music metadata
Overall, WP2 has been carried out through a collaborative and iterative process to obtain the first and second version of the different deliverables. The work carried out in WP2 has been distributed among the project partners according to their specific expertise, resulting in a complementary and coordinated effort towards the development of a standardized, trusted, and unified music metadata ecosystem / UPV, in close collaboration with BMAT and VU, has led the conceptual formulation and technical implementation of WP2, particularly the design and development of the distributed architecture of the Music360 platform. During the first deliverables version (V1), UPV has been responsible for defining the Music360 Ontology and the supporting Architecture together with VU (Deliverables D2.1 and D2.2). Thus, implementing the core backend components such as APIs, data ingestion pipelines, and integration services. In the second iteration (v2). UPV and BMAT further refined architecture by introducing a more modular and efficient technology stack, improving data processing capabilities, and supporting large-scale distributed data management. / VU has played a central role in the conceptual and security-related aspects of WP2. This includes the development and alignment of the ontology and data model with the project’s conceptual framework, as well as the design and implementation of the security framework (Deliverables D2.3 and D2.6). VU has defined authentication and authorization mechanisms, access control models, and data governance principles. In the second version, VU has also led the exploration and validation of privacy-preserving computation techniques, enabling secure data analysis across multiple stakeholders without disclosing sensitive information / BMAT has contributed mainly to data-related aspects and technical implementation support. Its work includes providing and handling real-world music data, developing data ingestion and transformation processes, and supporting metadata harmonization across heterogeneous sources. BMAT has also contributed to implementing and testing architectural components, ensuring the system can effectively integrate and process real-world industry data. / The different Music360 partners, including CMOs, have supported WP2 by aligning technical developments with value modeling requirements. Their contribution focuses on ensuring that the architecture and data structures adequately support the measurement of both the economic and non-economic value of music, as defined in the project. They have also contributed to requirements analysis and validation of the system design from a value network perspective. In particular, partners responsible for living labs execution have contributed by providing requirements, domain knowledge, and real datasets. They have participated in empirical validation activities, helping refine the architecture and ensuring the developed solutions align with real-world needs and constraints. / Description of work progress / The work carried out in WP2 has followed a structured, iterative process, progressing from conceptual design to implementation and validation, as reflected in both the defined tasks and their corresponding deliverables. / Tasks / T2.1a/b Designing an ontology for the value of music (Q2.2) (Lead: UPV; VU, BMAT). This leads to D2.1 and D2.4. The tasks require workshops with physical presence (WS2, WS5). / T2.1a/b focused on developing a common ontology for music metadata, defining the key entities, relationships, and value dimensions relevant to the music ecosystem. The ontology specification was iteratively improved through various workshops and working meetings, in which Music360 partners participated to assess the complexity of the music value chain. Attention was given to the experience of the participating CMOs regarding royalty distribution and the use of standards such as DDEx, as well as the role of TVE in aligning different perspectives within a common organizational model. / The outcome of this task was initially captured in D2.1, which introduced the first version of the ontology, mainly focused on the monetary value of music. It was later refined in D2.4, where the model was extended and aligned with stakeholders' needs, integrating new requirements for non-monetary values and more complex music analysis. / T2.2a/b Designing and implementing a platform for data collection and representation (Q2.1, Q2.5) (Lead: UPV; participants: VU, BMAT). This refers to M2 (M10) and M6 (M25), and D2.2 and D2.5. / T2.2 addressed the design and implementation of the data collection and representation architecture used as the backbone of the Music360 platform. The initial results of this work were documented in deliverable D2.2, which defined a baseline architecture incorporating core components such as APIs, data ingestion pipelines, and aggregation services. TVE, VU, and UPV mainly supported this initial version. / As the project progressed, this architecture was further refined and expanded in D2.5, which introduced version 2. Refinement of the Music360 architecture also involved BMAT, which provided a practical perspective on music usage and facilitated the process of enriching information about music to visualize music analysis. / This updated architecture supports decentralized data collection, enabling multiple data providers to contribute to the dataset while retaining control over their own data. It also ensures interoperability through shared schemes and open standards. Improvements in scalability, performance, and extensibility have also been incorporated, reflecting feedback from implementation and validation activities. Implementing the Music360 platform brought the concepts and designs proposed for the Music360 Ontology and Architecture, which have been validated by the CMOs involved in the project during different working sessions and demo days. / T2.3a/b Designing and implementing security mechanisms for controlled data access (Q2.3/Q2.4) (Lead: VU; participants: UPV, BMAT). This leads to D2.3 and D2.6. / The focus of T2.3 was to ensure secure and trusted data sharing within this distributed environment. The initial security framework, which included core mechanisms such as authentication, authorization, and access control, was defined in. In this task, the focus shifted towards enabling secure collaboration in multi-party and partially untrusted environments. Consequently, privacy-preserving computation techniques, such as secure multi-party computation, were explored. / Deliverables / D2.1: An ontology of the value of music – version 1. This is a machine-processable version of the conceptualization in D1.1. (UPV)(month 8) (R5). / The focus of Deliverable D2.1 was on representing the monetary value of music, as well as the concepts and relationships involved in music creation and royalty payments. To achieve this, initial ontology workshops were conducted in Amsterdam and Valencia to capture the complexity of the music value chain across the countries involved. This also involved analyzing the various data models currently used by CMOs to represent their music management information for royalty payments. / D2.2: A distributed architecture and implementation for music data collection, representation, and distribution -version 1. First version of a system to store and obtain data concerning the value of music in a distributed way, e.g., without using centralized information sources. Challenge is to include information sources from IPR societies, additional information collected by BMAT, and information from customer surveys (UPV) (month 10) (R6) / D2.2 provided the initial architecture that was primarily designed by VU and TVE, and was implemented alongside UPV and BMAT. This set of components captures data from various providers and loads it into a common data model based on the first version of the Music360 Ontology. Implementing specific APIs enabled users to control data loading and access according to their roles. This deliverable demonstrated the possibility of exchanging and analyzing data from CMOs in different countries and the possibility of enriching the music information (using BMAT technology) to obtain an overview of the monetary value of music in different venues. / D2.3: Secure and trusted sharing of music data – version 1. First version of a security architecture. The focus will be on authorization and access control of information stored at various sources (VU) (month 12) (R7) / D2.3. Included the use of standard protocols and the implementation of fine-grained access restrictions. It was relevant to make a proper characterization of music stakeholders and the roles supported in the Music360 platform. For this purpose, different workshops were performed with CMOs and other industry actors. / D2.4: An ontology of the value of music – version 2 / D2.4 improved the initial ontology definition (D2.1), taking into account the results of the living labs and the feedback received from the Music360 partners during the workshops held in Barcelona, Dublin, and Valencia. The Music360 Ontology v2 supports enriched analysis for further research and the empirical evaluation of the impact of music, as well as improving the characterization of the value of music from monetary and non-monetary perspectives. This evolution ensured that the ontology could support interoperability across heterogeneous data sources and the representation of complex value-related concepts. / D2.5: Deliverable D2.5 corresponds to the working prototype of the Music360 that demonstrates the feasibility of integrating multiple data sources, managing distributed data, and providing unified access and visualization capabilities. The implementation also incorporates the security mechanisms defined in T2.3 (D2.3 and D2.6), ensuring that the system is both functional and trustworthy. / D2.5 involved reengineering the initial architecture with technological components to support more demanding data loading scenarios, thereby improving the performance and response time of the original version when managing large volumes of music data. The second version of the Music360 architecture was mainly led by UPV in collaboration with BMAT. VU played a significant role in the validation process, aligning the requirements of the various stakeholders with the capabilities of the architecture by conducting demonstrations and validation activities with real users. / D2.6: Secure and trusted sharing of music data – version 2. This deliverable demonstrates the use of secure multiparty computing techniques for making information available to others. The deliverable corresponds to task T2.3. / The deliverable presents and implements the decentralized authentication architecture for the Music360 data sources. Currently, the music sector lacks a standardized authentication solution. The approach of Music360, based on OAuth 2.0 / OpenID Connect, allows data owners, such as CMOs, to stay in control of their own data. This is an innovation for the sector. We have also developed a prototype that shows how secure multi-party computing, specifically Prio+, can be used to calculate the average earnings of artists (e.g., by a policymaker) without exposing the artists' earnings. / Not in the deliverable, but still executed, is a design for keeping the relationship between IPI (author)and IPN (performer), as collected by the Music360 platform, secret while allowing its use in aggregated queries in a privacy-preserving way.

#### 1.2.3 Work Package 3 - Stakeholder-level reporting and analysis of the value of music
The main objective of WP3 was to design, develop, and deploy the Music360 digital platform—a comprehensive dashboard enabling diverse stakeholders (creators, CMOs, venue owners, researchers, and policy makers) to analyze the economic and societal value of music. Over the course of the project, WP3 successfully transitioned from the initial definition of user requirements and wireframes to the deployment of a fully functional, secure, and AI-enhanced production environment. / Description of work progress / The work progress in WP3 was structured around two major iterations of the dashboard: / 1. Initial design and architecture (Dashboard v1): During the first phase of the work package, the foundational architecture of the Music360 platform was established. This involved extensive collaborative workshops to define user stories and UI/UX wireframes (using Balsamiq) tailored to the specific needs of different music industry stakeholders. The technical development focused on building the front-end client and the back-end Aggregation Service. A secure authentication module using JSON Web Tokens (JWT) was integrated to manage access, and the system was successfully connected to the REST API of a resource server (including music usage data enriched by BMAT and participating CMOs). The platform offered authorization rules to ensure that non-public data was accessed only by authorized users (e.g., performers' revenues by the authenticated performer or affiliated CMO). / This phase culminated in a working production environment capable of ingesting and visualizing real venue data, fulfilling the objectives of Deliverable D3.1. / 2. Advanced architecture and security, qualitative integration, and AI capabilities (Dashboard v2): The second phase focused on scaling the platform to support a decentralized architecture, allowing the dashboard client to successfully connect to the federated REST APIs of multiple resource servers. This allowed the client to retrieve, aggregate, and display data controlled by different participants of the Music360 ecosystem, hosted in their own resource servers. On the other hand, V2 extended V1 to handle the complex intersection of "Open Science" mandates and commercial data privacy. A strict Role-Based Access Control (RBAC) matrix was implemented to enforce a "Permissioned Open Data" architecture. This ensured that sensitive granular data (such as specific revenue and plays) was restricted to authorized owners (e.g., creators viewing their own IPI/IPN assets, or venue owners viewing their own premises), while researchers and the public were granted access to dynamically masked, macro-level trends (e.g., genre, tempo, country analytics). / Furthermore, the dashboard's capabilities were expanded beyond quantitative analytics to include qualitative insights. A new "Studies" module was integrated, allowing stakeholders to browse the psychological and social value of music (such as the impact of licensed vs. copyright-free music) generated by the WP6 Living Labs. / Finally, to democratize access to these complex datasets, WP3 successfully integrated the "Research Explorer"—an autonomous, persona-aware AI agent powered by Large Language Models (orchestrated via Strands and AWS). This feature allows non-technical stakeholders to query both the quantitative API stats and the qualitative Living Lab studies using natural language. / The successful implementation of these advanced features marked the completion of Deliverable D3.2, fully realizing the WP3 mandate to provide unprecedented, legally compliant insight into the European music ecosystem. / Tasks / T3.1a/b Designing and implementing stakeholder data presentation tools (Q3.1/Q3.2) (Lead: BMAT; participants: VU). This results into M4 3(M15) and M8 (M31), D3.1 and D3.2. These tasks will have a physical workshop meeting (WS3, WS5) / This task focused on the front-end development, User Interface (UI), and User Experience (UX) of the Music360 dashboard. / Requirements & design: In collaboration with Stichting VU, physical workshops (WS3 and WS5) were organized to define user stories and specific UI requirements for the diverse array of Music360 stakeholders (creators, CMOs, venues, researchers, and policy makers). This process utilized collaborative wireframing tools (Balsamiq) to iterate on the design. / Implementation: BMAT led the implementation of the front-end client. For the v1 dashboard, this included building the foundational views, dynamic charts, and mapping tools. For the v2 dashboard, the front-end was expanded to integrate qualitative data (the "Studies" module) and the AI-driven "Research Explorer" chat interface. / Outcomes: The successful execution of this task resulted in the achievement of Milestones M4 (M15) and M8 (M31) and provided the user-facing application documented in Deliverables D3.1 and D3.2. / T3.2a/b Music360 platform value analysis and reporting tools (Q3.1/Q3.2) (Lead: BMAT; participants: VU). These tasks require a physical workshop, which will be co-located with WS3 and WS5. / This task focused on the back-end architecture, API integrations, and the data aggregation services necessary to power the front-end presentation tools. / Architecture & security: During physical workshops (co-located with WS3 and WS5), the technical requirements for the API endpoints and data federation were established. BMAT developed the core Aggregation Service, which securely fetches and processes data from distributed resource servers (including BMAT databases and participating CMOs). / Implementation: A critical achievement of this task was the implementation of the secure authentication and authorization module using JSON Web Tokens (JWT). In the second iteration of the project, this was expanded into a highly granular Role-Based Access Control (RBAC) matrix, ensuring that sensitive data is dynamically masked based on the user's logged-in persona (enforcing the "Permissioned Open Data" architecture). / Outcomes: This task established the robust, secure back-end infrastructure required to perform complex cross-border value analysis, directly supporting the platform functionality delivered in D3.1 and D3.2. / Deliverables / D3.1 Reusable dashboard to present and analyze the value of music - version 1. Web frontend for stakeholder-oriented modeling and value analysis. (BMAT)(month 15) (R8) / This deliverable documented the initial design, architecture, and deployment of the first iteration of the Music360 digital platform. It detailed the stakeholder-centric design process, including the formulation of user stories and the creation of UI/UX wireframes (via collaborative workshops). Technically, the report outlined the successful deployment of the web front-end client and the back-end Aggregation Service. Key achievements documented in D3.1 included the integration of a secure JSON Web Token (JWT) authentication module, the architecture design to connect to federated REST APIs from resource servers (including BMAT and CMO databases), and the deployment of a production environment capable of processing and visualizing real-world venue data. This deliverable successfully laid the foundation for Result R8. / D3.2 Reusable dashboards to present and analyze the value of music – version 2. A revisited version of the dashboard, including the lessons learned by the Living Labs. (BMAT)(month 31) (R8) / Building upon the foundation of v1, this deliverable documented the finalized, production-ready version of the Music360 dashboard, directly incorporating the lessons learned and data generated by the WP6 Living Labs. A major technical achievement detailed in this report was the implementation of a highly granular Role-Based Access Control (RBAC) matrix that operationalized the "Permissioned Open Data" model, balancing commercial privacy with open science. Furthermore, D3.2 documented the expansion of the platform to include qualitative data (via the new "Studies" module) and the successful deployment of the "Research Explorer"—an AI-driven LLM agent orchestrating natural language queries across the platform’s quantitative and qualitative datasets. The submission of D3.2 marked the complete fulfillment of the WP3 mandate and the final realization of Result R8.

#### 1.2.4 Work Package 4 - Ecosystem-level reporting and analysis of music value creation, distribution and consumption
This work package focuses on developing software tooling to (re)design business ecosystems, following the e3value method. The method and the associated tooling were used in WP5 to design the ecosystem for the Music360 platform. Additionally, in WP6, we developed and analyzed the RAAP/PPI case with the e3value method. / Description of work progress / While individual stakeholders are interested in transparency of value creation, distribution, and consumption of music in which they are involved, policymakers and strategic planners are interested in collecting information about the entire ecosystem. For example, policymakers are interested in the royalty cash flow across national borders, or in the international distribution of locally produced music. This ecosystem-level information is aggregated and anonymous. / In Music360, we reengineered the e3web software tool for ecosystem modeling, incorporating the e3value notation into the Ecosphere toolset, which can be securely fed with data from the Music360 platform. Development was done at the VU (for security mechanisms), TVE (for the development of the Ecosphere tool), and BMAT (for the relation with the stakeholder-level dashboard). In addition to the in-person project meetings where we coordinated work, we held weekly online meetings with all developers to ensure consistent progress. / Our work on Ecosphere breaks down into the following tasks. / Tasks / T4.1 Designing and implementing graphical ecosystem modeler tool (Q4.1) (Lead: TVE; participants: VU, BMAT) . / We tested the ecosystem modeling language e3value on the music ecosystem by producing an e3value model for the music ecosystem of each country participating in Music360. We generalized this into a generic EU model and extended it with an ecosystem model for the Music360 platform. These exercises showed that e3value is powerful enough to represent the EU music ecosystem. / We also overhauled the existing e3value toolset (e3web) into a more user-friendly, web-enabled system, Ecosphere, with a plug-in architecture that can facilitate data feeds from the various CMOs in the project that make data available to the Music360 platform. / T4.2 Extending ecosystem modeler tool for full support of the e3value language (Q4.1) (Lead: TVE; participants: VU, BMAT). / To create full support for e3value we reengineered the e3value metamodel and implemented it in Ecosphere. This includes adding a transaction editor and a reporting pane that displays warnings and errors during ecosystem modeling and analysis. We also adapted the numerical execution engine of e3web for Ecosphere to generate ecosystem-level value flow analysis, including cash flow analysis for the entire ecosystem. / We revised the backend structure of e3web, now Ecosphere, completely, to comply with the chosen security architecture. First of all, this means that we introduced OAuth2/OpenID Connect authentication in the platform, in the way proposed in deliverables D.2.3 and D2.6. This also resulted in a completely new implementation of the backend platform using resource sources (according to the OAuth 2.0 terminology). / T4.3 Ecosystem tooling extended with secure access to live music value data feeds (Q4.2/Q4.3) (Lead: TVE; participants: VU, BMAT). / We have demonstrated with the RAAP/PPI case study (see also D6.6) that the Ecosphere toolset can perform calculations of interest to policymakers. An example of this is the amount of money that shifts from Rome Treaty performers to non-Rome-treaty performers as a result of the RAAP/PPI verdict. The analysis, based on the Music360 data, requires a human step, as the data from the Music360 platform is not directly suited to ecosystem-level calculations, and the translation of Music360 usage into data usable in the Ecosphere toolset is highly domain-dependent. / Deliverables: / D4.1: Dashboard for ecosystem modeling – version 1. Software tooling to model music ecosystems, including valuation assessment on the ecosystem level. Focus on graphical modeling of monetary and non-monetary value flows in an ecosystem. / Deliverable D4.1 concerns the revised graphical editor, which runs in the web browser and therefore no longer requires the end user to install software. Furthermore, the deliverable is about the implementation of the net value flow calculation for each actor in the business ecosystem. This allows us to do financial sustainability assessments on the actor level. Finally, we changed the platform's backend to fit the Music360 architecture. / We documented the Ecosphere system in D4.1. / D4.2: Dashboard for ecosystem-level value analysis -version 2. Focus on the inclusion of data feeds on the value of music. / A browser component was developed to offer created e3value models to users in a structured way. This concerns frontend development in Angular. Similarly, a new workspace for users was developed. / We migrated the platform to a microservice architecture (which is the foundation for the overall Music360 architecture). The microservice architecture implements a plugin system, in which functionality can be added to or removed from the platform. / We further developed an automated financial assessment of the business ecosystem on a per actor basis. Access control is fully implemented by the database management system using Row Level Security. Again, this follows the guidelines as specified by the Music360 security architecture, and it ensures that security operates directly on the data to be protected, rather than derived artifacts. This meets the stakeholders' requirements if the platform provider is a trusted party. / A model was developed for the RAAP/PPI case, a court verdict concerning the eligibility of non-Rome treaty productions for neighboring rights. It serves as an interesting example for policymakers of how the effects of laws and court verdicts can be analyzed at the level of the business ecosystem. To do so, we collected data on the number of plays of recordings from the Dutch living lab and used it to inform the music ecosystem's business model. The connection is semi-automated; data is extracted from the database in accordance with the Music360 database model. Then it is converted into a format that Ecosphere and the e3value model can understand. This conversion is semi-automatically: the data provided is in a very different format from that required by the e3value model. Nevertheless, we have demonstrated that it is possible to use collected data from the living lab in ecosystem-level analysis using Ecosphere. / All this is documented in D4.2.

#### 1.2.5 Work Package 5 - Sustainable business model of Music360 solution
Description of work progress / Within our project framework, WP5 has demonstrated substantial progress by forming a dedicated working group that convenes regularly to coordinate the development of deliverables 5.1 and 5.2 and address strategic milestones. Under the leadership of SENA, these sessions have fostered a structured and inclusive environment, with partners such as TVE, VU, BMAT, BUMA, GDA, and IMRO actively contributing to identifying sustainable business models for the Music360 platform. / The collaborative approach initiated by WP5 began with a comprehensive mapping of potential platform users, encompassing not only music IP right holders, venues, and policymakers, but also extending to a broader spectrum, including other IP CMOs, music marketers, and scholars. This inclusive overview enabled the team to better understand Music360's diverse use cases and value propositions. / Throughout these sessions, partners engaged in in-depth analysis of governance structures and cost models, evaluating various scenarios for ownership, management, operationalization, and ongoing maintenance of the platform. These discussions drew upon best practices from established industry entities such as DDEx, CISAC, and SCAPR, whose operational models and international reach provided valuable benchmarks for sustainable platform development. / In addition, WP5 placed significant emphasis on adoption strategies, focusing on ensuring widespread engagement and data contributions from relevant stakeholders. To this end, consortium partners initiated direct outreach to key organizations, with authors’ CMOs liaising with CISAC and GDA, and SENA engaging with SCAPR. These efforts have included multiple in-person demonstrations and remote follow-ups, ensuring the Music360 platform’s value is communicated effectively to the broader community. / Progress and outcomes from these coordinated activities have been shared regularly among consortium members, ensuring transparency and alignment across work packages. Key developments, stakeholder feedback, and future requests are addressed in monthly meetings, fostering ongoing collaboration and synergy within the project’s ecosystem. / Tasks / T5.1a Designing and validating Music360 platform business model v1. Focus on a sustainable business model. (Q5.1/Q5.2) (Lead: SENA; participants: TVE BUMA, BMAT, GDA, IMRO) . This results in D5.1. This task requires a physical workshop (WS2). / The task force initiated a series of collaborative sessions to establish a sustainable business model for the Music360 platform. This process began with a comprehensive mapping of potential users, identifying a wide array of stakeholders, including music IP right holders, venues, policymakers, other IP CMOs, music marketers, and scholars. Through structured dialogue, the team explored diverse use cases and the unique value propositions the platform could deliver. In addition, the group critically evaluated governance and cost models, drawing on industry benchmarks to ensure operational viability and long-term sustainability. For further details on the methodologies and outcomes, please refer to Deliverable D5.1. / T5.1b Designing and validating Music360 platform business model v2. Focus on scaling up. (Q5.3) (Lead: SENA; participants: TVE, BUMA, BMAT, GDA, IMRO). This leads to D5.2. This task requires a physical workshop (WS5). / Building on the groundwork laid in T5.1a, the team shifted its focus to strategies for scaling the platform. Key efforts included reviewing adoption scenarios to promote broad and meaningful stakeholder engagement and ensuring robust data input to maximize platform value. The consortium actively engaged with leading industry organizations, such as CISAC and SCAPR, and conducted multiple demonstrations and feedback sessions to support widespread adoption. These activities formed the basis for refining governance and cost models, facilitating a scalable and resilient business framework. For a comprehensive account of these activities and recommendations, consult Deliverable D5.2. / Deliverables: / D5.1 Sustainable business model of Music360 dashboard – version 1. A sustainable ecosystem business model of the Dashboard and data collection mechanisms of the four participating countries, tested in simulations. (SENA)(Month 16) (R10) / Deliverable D5.1 presents version 1 of a sustainable ecosystem business model for the Music360 Dashboard, defining how value is created and captured for key stakeholders and how the platform can remain viable beyond the project lifetime. It describes the proposed governance and revenue options for operating the Dashboard as a multi-actor data platform and specifies the associated data collection and sharing mechanisms implemented across the four participating countries. The deliverable also outlines how these cross-country mechanisms and business-model scenarios are validated through simulations, providing early evidence on feasibility and sustainability assumptions. / D5.2 Sustainable business model of Music360 dashboard – version 2. A revised and scalable, validated business model for the Dashboard, based on experiences and interviews in WP6. (SENA)(Month 32) (R10) / Deliverable 5.2 outlines a sustainable business model for the Music360 Dashboard (version 2) developed within the EU Horizon Europe Music360 project. It describes what the Music360 ecosystem currently consists of (specifications plus a demonstrator prototype) and derives value propositions and deployment paths for key artifacts: (1) an industry-level ontology and relational data model that links rights holders, works (ISWC) and recordings (ISRC) and supports richer international usage/revenue transparency; (2) a distributed, security-focused reference architecture (OAuth2/OpenID-based authentication, data services, data integration, aggregation services, and advanced privacy-preserving computation using SMPC/HE); (3) user-facing frontends and an LLM-based search capability over deliverables and Living Lab results and (4) an Experimentation ToolKit to replicate and run quantitative experiments on the value of music / The document identifies prospective adopters such as umbrella organizations (SCAPR, CISAC), CMOs, music data providers, venues and policymakers. Several components (ontology, architecture) are intended to be openly reusable, while recurring funding is primarily for operating shared services (e.g., authentication proxy, platform subscriptions) and value-added offerings (frontends, experimentation support, policymaker access). It highlights concrete deployment of drivers, such as unifying author and performer identities (linking IPI and IPN) and improving cross-border transparency, and discusses scenarios, including a European Music Observatory as a potential long-term home for governance and maintenance. Finally, it notes that the current platform is a proof of concept and sketches a phased route to production readiness (requirements & gap analysis; rebuild and legal/security hardening; implementation/testing in local systems; onboarding), with an indicative technical cost of about €1M excluding legal and rollout-related expenses.

#### 1.2.6 Work Package 6 - A field validated Music360 solution
Description of work progress / This work package is about a series of experiments in Finland, the Netherlands, Ireland, Spain, and Portugal. / Tasks / T6.1a/b Eliciting stakeholder needs for the understanding of music (Q6.1) (Lead: IMRO/GDA; participants: TVE, SENA, BUMA, GTM, IMRO, Aepo-Artis). This refers to D6.1, and D6.2. / Task T6.1 addressed the elicitation of stakeholder needs related to the value of music, covering both national and international perspectives. Task 6.1a was implemented through a workshop with physical attendance, co-located with the project kick-off event (WS1), enabling structured engagement with representatives of collective management organizations and related stakeholders. Task 6.1b was carried out through a second workshop, co-located with a later consortium event (WS5), to refine and extend the initial requirements, with particular attention to cross-border and international aspects. The outcomes of these activities informed Deliverables D6.1 and D6.2, which document stakeholder requirements for national and international living labs, respectively. / T6.2 Modeling national ecosystems (Q6.2) (Lead: TVE; participants: SENA, BUMA, GDA, GTM, IMRO). This leads to D6.3. / Task 6.2 focused on the modeling of national music ecosystems in participating countries. A workshop with physical attendance (WS2) was organized to support a shared understanding of national value networks, actors, exchanges, and dependencies. Consortium partners contributed domain-specific knowledge to identify relevant stakeholders, rights flows, data sources, and interactions within each national context. The work resulted in structured ecosystem representations that served as the conceptual basis for subsequent technical implementation and validation activities and directly contributed to Deliverable D6.3. / T6.3 Expressing national ecosystems in ecosystem modeler (Q6.2) (Lead: TVE) / Building on the conceptual models developed in Task 6.2, Task 6.3 translated national music ecosystems into formal representations using the ecosystem modeling tool. This work involved encoding actors, value exchanges, and relationships. The resulting models enabled comparison across national contexts and provided a stable reference for data integration, dashboard design, and validation activities in later tasks. / T6.4 Defining national field validators. This also includes the recruitment of music rights users and owners who participate. (Q6.2) (Lead: GDA; participants: SENA, BUMA, GTM, IMRO). This task requires a workshop with physical presence (WS2). / Task 6.4 established the framework for national field validation by defining validation scenarios and recruiting participating music rights users and rights holders. This task included a workshop with physical presence (WS2), organized jointly with ecosystem modeling activities, to align validation objectives with national ecosystem characteristics. Participants were selected to reflect different roles within the music value chain, ensuring that validation activities addressed practical use cases relevant to the Music360 solution. / T6.5 Designing and implementing national data feeds (Q6.2) (Lead: GDA; participants: SENA, BUMA, GTM, BMAT, UPV, VU, IMRO) / Task 6.5 addressed the design and implementation of national data feeds required to support the Music360 dashboards and living labs activities. Partners collaborated to identify relevant data sources, define data structures, and implement data ingestion pipelines aligned with national ecosystem models. The work ensured interoperability between heterogeneous data sources and established the technical foundation for national living lab demonstrators by enabling consistent data collection and processing. / T6.6 Designing and implementing national Dashboards (Q6.2) (Lead: BMAT; participants: VU, UPV). / Task 6.6 focused on the design and implementation of dashboards supporting the national living labs. A physical workshop (WS3) was held to align dashboard requirements with stakeholder needs and available data feeds. The dashboards were implemented to visualize key indicators derived from national ecosystem models and data streams, supporting exploration and analysis by field validators. This task complemented data feed implementation and contributed to the overall national demonstrator. / T6.7 Validating the Music360 solution in the national fields (Q6.2) (Lead: GDA; participants: SENA, BUMA, GTM, BMAT, UPV, VU, IMRO). Tasks T6.4, T6.5, T6.6, and T6.7 result in demonstrator D 6.5 / Task 6.7 carried out the validation of the Music360 solution in national contexts using the implemented dashboards and data feeds. Validation activities involved field validators identified in Task 6.4 and were conducted in collaboration with technical and domain partners. Feedback from these activities was collected to assess the alignment between stakeholder needs, ecosystem models, and technical implementations. Tasks T6.4, T6.5, T6.6, and T6.7 together resulted in the national living lab demonstrator documented in Deliverable D6.5. / T6.8 Modeling international ecosystem (Q6.3) (Lead: TVE; participants: SENA, BUMA, GDA, GTM, IMRO). This leads to D6.4. / Task 6.8 extended ecosystem modeling activities to the international level, focusing on cross-border interactions and aggregated value flows. A workshop with physical attendance (WS5) supported the identification of international actors, relationships between national ecosystems, and shared dependencies. This work resulted in a coherent international ecosystem model capturing interactions beyond national boundaries and formed the basis for Deliverable D6.4. / T6.9 Expressing international ecosystem in ecosystem modeler (Q6.3) (Lead: TVE) / Task 6.9 translated the international ecosystem model developed in Task 6.8 into the ecosystem modeling tool. / T6.10 Defining international field validator. This also includes the recruitment of music rights users and owners who participate. (Q6.3) (Lead: GDA; participants: SENA, BUMA, GTM, IMRO). This task requires a workshop with physical presence (WS6). / Task 6.10 defined the international field validation framework, including the recruitment of music rights users and rights holders operating in cross-border contexts. A workshop with physical presence (WS6) was organized to align validation scenarios with international ecosystem characteristics and technical constraints. This task ensured continuity between national and international validation activities and prepared the ground for integrated testing of the Music360 solution. / T6.11 Unifying national data feeds (Q6.3). In this task, the resulting demonstrators (D 6.5) will be changed to be useful in an international context (Lead: GDA; participants: SENA, BUMA, GTM, BMAT, UPV, VU, IMRO) / Task 6.11 focused on adapting and unifying national data feeds to support the use cases. Existing national demonstrators were modified to ensure consistency, comparability, and interoperability across countries. This work enabled aggregated analysis and cross-border visualization by aligning data definitions, processing logic, and interfaces, thereby extending the applicability of Deliverable D6.5 to an international context. / T6.12 Designing and implementing international Dashboard (Q6.3) (Lead: BMAT; participants: VU, UPV). This task requires a physical workshop (WS5). / Task 6.12 addressed the design and implementation of a dashboard for the living labs. A physical workshop (WS5) was held to align dashboard functionality with international validation requirements and unified data feeds. The dashboard provided access to indicators derived from the international ecosystem model and enabled analysis across multiple national contexts. / T6.13 Validating the Music360 solution in the international field (Q6.3) (Lead: IMRO; participants: SENA, BUMA, GTM, BMAT, UPV, VU, GDA). / Task 6.13 validated the Music360 solution in an international context through a physical integration workshop (WS6). Validation activities involved international field validators and focused on the integrated operation of ecosystem models, data feeds, and dashboards. Feedback collected during this task informed the assessment of system behavior in cross-border scenarios and led to the international living lab demonstrator documented in Deliverable D6.6. / T6.14 Public OpenAPI access to living lab data. (Lead: BMAT; participants: VU, TVE, SENA, BUMA, UPV, GDA, GTM, IMRO). This leads to D6.7. / Task 6.14 implemented controlled public access to living lab data through an OpenAPI interface. This work defined access mechanisms, data exposure rules, and technical interfaces enabling external reuse of selected datasets generated within national and international living labs. The resulting API supports transparency and reuse while maintaining governance constraints and is documented in Deliverable D6.7. / Deliverables: / D6.1 Stakeholder needs for understanding the value of music – version 1. This deliverable comprises the requirements of stakeholder needs with respect to understanding of the value of music. Focus is on the national living labs. (IMRO)(month 2) (R1) / Deliverable D6.1 documents the requirements derived from stakeholder needs related to the understanding of the value of music, with a focus on national living labs. The deliverable is based on structured stakeholder engagement activities, including workshops and consultations conducted at an early stage of the project. It identifies information needs, decision contexts, and use cases relevant to national music ecosystems, providing a requirements baseline to guide ecosystem modeling, data integration, and dashboard design in subsequent tasks. The deliverable was completed in month 2 and served as an input for the design of national validation activities. / D6.2 Stakeholder needs for understanding the value of music – version 2. Focus is on the international living lab. (GDA) (month 18) (R1) / Deliverable D6.2 extends the stakeholder requirements analysis to the international living lab context. Building on the structure and findings of D6.1, this deliverable incorporates additional requirements arising from cross-border use cases, international rights flows, and aggregated ecosystem analysis. The document reflects stakeholder input collected through later project workshops and coordination activities, ensuring continuity between national and international perspectives. D6.2 was completed in month 18 and provides the requirements framework for international ecosystem modeling and validation. / D6.3 National music ecosystem models (month 8). Understanding of the national ecosystems by means of e3value ecosystem models. (TVE)(R11) / Deliverable D6.3 presents formal models of national music ecosystems developed using the e3value modeling approach. The deliverable captures key actors, value exchanges, and dependencies within each national context, based on input from consortium partners and stakeholder workshops. These models provide a structured representation of national ecosystems and support a shared understanding of value creation and distribution mechanisms. D6.3 was completed in month 8 and serves as a conceptual and technical reference for national data feeds, dashboards, and validation activities. / D6.4 International music ecosystem models. Understanding of the international ecosystem by means of the e3value ecosystem models. (TVE) (month 24) (R11) / Deliverable D6.4 documents the modelling of the international music ecosystem using e3value representations. The deliverable integrates interactions between national ecosystems and represents cross-border value exchanges and stakeholder roles. It builds on the national models developed in D6.3 and aligns them within a unified international framework. Completed in month 24, D6.4 supports the implementation of international data integration, dashboards, and validation scenarios. / D6.5 National living labs. Implementation of the dashboards and associated data collection mechanisms, and validation in national contexts. (GDA)(month 16) (R12) / Deliverable D6.5 describes the implementation of national living labs, including dashboards, associated data collection mechanisms, and validation activities conducted in national contexts. The deliverable also includes the presentation of the conclusion of the different national living labs conducted until this period, and the lessons learned by conducting the first iteration of the national living labs. The deliverable documents the technical setup of data feed and the execution of national living labs. Completed in month 16, D6.5 demonstrates the operational use of the Music360 solution at the national level and the living labs experiences held. / D6.6 International living lab. Implementation of the dashboards and associated data collection mechanisms, and validation in an international context. (IMRO) (month 36) (R12) / Deliverable D6.6 documents the implementation and validation of the international living lab. This includes the integration of unified data feeds, the deployment of an international dashboard, and validation activities conducted in cross-border contexts. The deliverable D6.6 also reported on the second iteration of the national living labs performer in the different countries, presenting the data, conclusions, and lessons learned in the second iteration of the national living labs. D6.6 was completed in month 36 and represents the final validation stage of the Music360 solution. / D6.7 Open data access living labs. Public API-controlled access to data found in the living labs. (BMAT)(month 36) (R12) / Deliverable D6.7 describes the implementation of public, API-controlled access to selected data generated within the national and international living labs. The deliverable documents the design of the OpenAPI interface, access mechanisms, and governance constraints applied to data exposure. Completed in month 36, D6.7 enables controlled reuse of living lab data by external stakeholders while maintaining alignment with project data management and governance requirements.

#### 1.2.7 Work Package 7 - Dissemination, communication and exploitation
Work Package 7 (WP7) ensured the effective communication, dissemination, and exploitation of Music360 project results, targeting stakeholders across the European music ecosystem. From an excellence perspective, WP7 implemented a structured and adaptive dissemination strategy aligned with Horizon Europe requirements and stakeholder needs. From an implementation perspective, dissemination activities were coordinated across partners through defined roles, workflows, and tracking mechanisms, ensuring consistency and efficiency. From an impact perspective, WP7 significantly enhanced the visibility and uptake of project results through stakeholder engagement, event participation, and scientific dissemination. During implementation, the communication strategy was refined following discussions with the European Commission to better align with industry practices and evolving digital communication channels. Minor delays in some dissemination-related deliverables did not affect the overall communication objectives or impact. Detailed dissemination results and outputs can be found in the relevant WP7 deliverables / Description of work progress / Within our project framework, significant progress has been achieved through the establishment of a dedicated task force that convenes biweekly to strategize upcoming deliverables and ongoing dissemination efforts. The coordination of these meetings is led by VU Amsterdam, which leverages a collaborative approach in which responsibilities are distributed among participating partners. / BMAT has taken the lead in managing website content and updates, ensuring a cohesive online presence reflective of project objectives. Furthermore, collaborative efforts between SENA and BUMA are instrumental in drafting PR materials tailored for events showcasing Music360, maximizing outreach and engagement opportunities. Finally, it is a shared responsibility among all partners to showcase Music360 during events. To ensure alignment across work packages and facilitate collaboration, key highlights and relevant requests are shared during monthly project meetings, fostering synergies throughout the project. / Tasks / T7.1 Plan for the dissemination and exploitation of results (Lead: BUMA). This leads to D.7.1 / The task force developed a comprehensive communication and dissemination strategy to streamline outreach and engagement. This involved defining clear communication objectives, identifying stakeholders, and strategically selecting communication channels to effectively engage them. Moreover, the strategy incorporates considerations to maintain a consistent tone of voice and foster inclusivity. For a deeper insight into these strategies, please consult the relevant Deliverable document. / T7.2 Project website (Lead: BMAT). This leads to D 7.2 / The project website has launched, marking the beginning of a continuous effort to provide regular updates. While facing initial challenges, we have overcome hurdles and are now consistently updating the website. Additionally, we are enhancing its appeal by regularly publishing blog posts that add a personal touch to the platform. / T7.3 Communication, e.g. press releases, presence on social media. / Music360 has selected LinkedIn, Facebook, and Instagram as its primary social media channels. Moreover, the task force is dedicated to leveraging local media and issuing press releases to enhance outreach. / T7.4 Dissemination at music industry events (e.g. EuroSonic Noorderslag and Westway lab) (Lead: SENA; participants: BUMA, GDA, GTM, TVE, BMAT, IMRO). This refers to M9 (M12), M10 (M24), and M11 (M32). / Music360 organized panels at EuroSonic Noorderslag (ESNS) 2024, 2025 and 2026. ESNS is of the most important music industry events in Europe. The project was also present at Westway lab in Portugal. In 2025, Music360 participated in a panel organized by GEMA (German authors' rights society) at the Reeperbahn festival in Hamburg. / T7.5 Dissemination at other organizations (e.g. branch organizations like SCPAR, CISAC, WIPO, and IFPI, and government, creators and users of music) (Lead: BUMA; participants: SENA, GDA, GTM, IMRO, Aepo-Artis) . This refers to M12 (M12), M13 (M24), and M14 (M32). / The (intermediate) results were presented at several SCAPR events in 2024 and 2026. The chairman of SCAPR was also present at the final event of Music360 in the EU parliament. The project was also presented at a general assembly meeting of CISAC. AEPO-ARTIS reported frequently (via newsletter reports and in person events) to its 42 performer CMO members, representing 650 000 performers throughout Europe. Progress in the project was shared via the AEPO-ARTIS social media channels, together with a contribution to the Music360 blog. / T7.6 Scientific dissemination (Lead: Stichting VU, participants: UPV) / The project published 35 peer-reviewed scientific publications, 3 publications in progress, 7 MSc theses, and contributions to 2 PhD theses. / T7.7 Roundtables European Commission (Lead Stichting VU, participants SENA, BUMA, GDA, GTO, IMRO, Aepo-Artis). This refers to M15 (M18) and M16 (M36) / The project contributed to a round table of the OpenMuse project, and the Music360 project organized a roundtable closing event in the European parliament. / Deliverables: / D7.1 Dissemination, communication, and exploitation plan version 1 (Stichting VU) (month 6)(R13) / The first version of the dissemination, communication, and exploitation plan introduced the communication objectives, the target audience, the publication strategy including the tone of voice. / D7.2 Dissemination, communication, and exploitation plan version 2 (Stichting VU) (month 18)(R13) / This deliverable concerns a revised version of the dissemination, communication, and exploitation plan. The task force was engaged in developing the second iteration (D7.2). The objective was to enhance the strategy by incorporating lessons learned from the first version and refining its components for improved effectiveness. / D7.3 Intermediate Policy Brief (BUMA)(month 15)(R13) / Halfway through the project, Music360 published an intermediate policy brief. The most important recommendations are: / Awareness of the cultural and societal value of music must be increased. / There is a need for harmonization of the legal provisions that are given to the different types of right-holders in the music sector. / There is a need for an EU-wide policy on the unlocking of data created but retained by digital music service providers. / D7.4 Final Policy Brief (SENA)(month 36)(R13) / Music360 published a final policy brief. The most important findings are: / Finding 1. Our empirical research has shown that music has economic, societal, and cultural value for many stakeholders. / Finding 2. There is a desire to consolidate more detailed information specific to the music sector, but no individual actor has the resources to develop this on their own or the capacity to do it at the EU level. / Finding 3. It is possible to create a decentralized data and knowledge sharing platform where data control remains with the data owner for the benefit of understanding the value of music. / Finding 4. Valuable data exists and can be aggregated across the EU, but it is not publicly available. Inclusion of this data within the cultural data hub would allow commercial users (shops, bars, etc.), music makers, and policy-makers to benefit from this / D7.5 Final report on communication, dissemination, and exploitation (month 36)(R13) / This deliverable contains an overview of all dissemination and communication results, including 14.275 website visits, 70215 LinkedIn impressions, 32 events, 7 demos, 5 podcasts, 11.900 views of the project’s video, 12 press releases, 12 radio & television appearances, and 2 university demos. / D7.6 Dissemination, communication, and exploitation plan version 3 (VU) (month 34)(R13) / This deliverable concerns a revised version of the dissemination, communication, and exploitation plan. It mainly includes an updated list of all publication trackers, and therefore shows the (nearly) final dissemination and communication result.

#### 1.2.8 Work Package 8 - Project management and data management
​​Description of work progress / Work Package 8 (WP8) ensured the effective coordination, governance, and administrative implementation of the Music360 project in full compliance with the Grant Agreement and the Description of Action. / From an implementation perspective, WP8 established and maintained a robust governance structure, including the General Assembly, Executive Board, and coordination mechanisms. Regular meetings and reporting ensured alignment across work packages and timely monitoring of progress. / From an excellence perspective, WP8 ensured high-quality execution through structured coordination, adherence to agreed procedures, and alignment with project objectives. / From an impact perspective, effective management enabled the successful delivery of project results across all work packages. While minor delays occurred in the submission of a limited number of deliverables, these were managed effectively and did not affect the overall results or impact of the project. / Overall, WP8 provided a stable and efficient framework for project execution. Detailed results of technical work can be found in the respective work package deliverables. / Deliverables: / D8.1 Management handbook (VU) (month 3) / We delivered a project management handbook, which, together with the Consortium Agreement, states the procedures and rules of engagement clearly. / D8.2/D8.3/D8.4 Data management plan beginning of project (VU)(month 6/18/36) / The initial data management plan was updated regularly.

#### 1.2.9 Work Package 9 - Ethics requirements
The objective of WP9 has been to ensure compliance with the 'ethics requirements' recommended by the Project Officer. / Description of work progress / WP9 has developed the deliverables for ensuring personal data protection in the living labs. It has given the consortium recommendations to proactively self-monitor the experiments. The support of the External Ethics Board during the process has clarified some of the concerns around personal data protection during research and the necessity of anonymization/pseudonymization of participants' personal data among the partners. / Deliverables: / D9.1 H - Requirement No. 1 (VU) (month 2) / D9.1 developed the procedure for recruiting, informing and protecting the personal data of the participants in the living labs. The steps proposed by UPV to the partners were: / While selecting the participants, work with the venues to identify/recruit them, considering the GDPR and avoiding bias. / Ask for approval from the universities or hospital ethics committees. / For CMOs, consider your own personal data protection policies. / Inform the participants about their personal data rights and provide content forms when necessary. / D9.2 POPD - Requirement No. 3 (VU) (month 2) / D9.2 was a support for the living labs when processing the personal data of the participants. It started providing main concepts on data protection, such as the data minimization principle. Then, based on the previous experiences of VU and UPV, it gave some recommendations to the partners: / To preserve the rights and freedoms of the data subjects/research participants. / To provide security measures to prevent unauthorized access to personal data or the equipment used for processing. / The necessity to implement anonymization/pseudonymization techniques. / Some templates were provided by UPV as an example of an informed consent form and information sheet to guide the partners. These templates stressed the importance of adding all the necessary information from the researchers as well as from the DPO involved. / The aim of the project has been that all the primary data collected in the living labs will be available only to the partner-researcher doing the experiment, and only anonymized results will be shared with the partners. / D9.3 AI - Requirement No. 4 (VU) (month 2) Ethics Handbook deliverable / The Ethics Handbook included general principles that complemented D9.1 and D9.2. It especially highlighted the prevention and mitigation of bias during the entire research process. Moreover, it specified that any interaction with an AI system/technology could not involve personal data. / D9.4 OEI - Requirement No. 5 (VU) (month 1) Creation of the project Ethics Board / The external Ethics Board has supervised the procedures used in the living labs to ensure the protection of participants' personal data. Before M6, M14, and M36, UPV sent them all the available documents to review. The interdisciplinarity of these three professionals has allowed the consortium to have a holistic perspective of the risks to avoid or mitigate. / Professor Marieke L. Fransen has given support from a human-centered approach during the research and design process. Mr. José Manuel López has given legal advice from a proactive risk-based approach. And Mr. Christos Bellos has provided a transparent and quality approach, especially in the case of health data. / D9.5 OEI - Requirement No. 6 (VU) (month 6) Ethics Board report – 1 / In this first report the experts reviewed D9.1, D9.2, D9.3 and all the documents involved. They made us some recommendations that were included in those deliverables to provide a clearer information to the potential participants and to ensure risks minimization. / D9.6 OEI - Requirement No. 7 (VU) (month 13) Ethics Board report – 2 / At this stage of the project, we sent to the experts D8.2 (Data Management Plan), Approvals from the Research Ethics Boards of the universities (VU and UPV), some documents from the living labs, and (just to clarify some points) the first version of D2.3 (Secure and trusted sharing of music data). / From all these documents, the Experts agreed that the project was complying with the regulations on personal data protection with a proactive ethics approach. Anyway, they made some recommendations to review D8.2. / D9.7 OEI - Requirement No. 8 (VU) (month 36) Ethics Board report – final / Due to its relevance, the last report was focused on the hospital living lab developed by UPV and Hospital Vithas in Valencia (Spain). All the necessary documents were sent to the experts by UPV, translating the protocols into English for providing a complete understanding. / Hospital Vithas followed the recruitment process and UPV research team only accessed the anonymized results that the patients filled in in no-digital paper sheets. Therefore, the research team didn’t collect the information from the patients that was retained by the hospital. In this sense, the Board suggested that the hospital could conduct a Data Protection Impact Assessment (DPIA). Although a DPIA was not mandatory regarding the activity carried out by this living lab, it could be recommended to them.

#§WRK-PLA-WP§# #@IMP-ACT-IA@#
### 1.3 Impact
The scientific impact of Music360 has been realized by peer-reviewed publications in scientific conferences. Our results in data- and value modeling have been published in flagship conceptual modeling conferences (IEEE Conference on Conceptual Modeling, IEEE Requirements Engineering Conference, International Conference on Model-Driven Engineering Languages and Systems). Our experience in the application of secure multi-party computing, as well as with decentralized engineering of the Music360 platform, has been published at the Requirements Engineering conference and the Ibero-American Conference on Software Engineering. Empirical results on the value of music have been published at marketing and Advertising conferences. / The societal impact of Music360 consists of the improved use of music by venues (shops, hotels, bars, etc.), improved insight into musicians' use of their music across Europe, and improved quality of decision-making about music by policy makers based on evidence. We have shown that these results are achievable. But they will not automatically materialize after Music360 is finished. For this to happen, CMOs need to support the development and uptake of the Music360 platform. / The Music360 living lab results have become visible and appreciated by the international music sector. This is, for example, demonstrated by GEMA, a large German CMO on author rights. They related their own music impact study to the Music360 living lab results, to help to create international awareness of the value of music. / Using the Music360 platform will not increase CMOs' revenue, but it will (to repeat) improve the use of music by venues, improve insight into the use of musicians' music across Europe, and improve the quality of evidence-based decision-making about music by policymakers. Musicians will improve their career planning, the use of music in Europe will become more transparent to decision-makers, and venues will be able to improve their branding and revenue. CMOs will be able to provide a better service for musicians. Because the benefit of the platform accrues to different stakeholders in society, while the effort to implement it is borne by CMOs, we recommend an initial subsidy from the EU to reduce the cost to CMOs of implementing the platform. / The platform has an economic impact on the revenue of musicians and venues where their music is played. It is also an innovative mechanism to solve a long-standing problem with relating author rights and neighboring rights. Thanks to fingerprinting technology, it will also provide insights into the use of AI-generated music in venues and its value to venues.

### 1.4 Update of the plan for the exploitation and dissemination of results
As indicated earlier, the Music360 platform would be a good start for a European cultural data hub, possibly combined with the OpenMuse sister project. Conversations with umbrella organizations, most notably CISAC, showed interest from the music sector in contributing to such a hub. However, we have also learned that the CMOs can not carry the costs for such a hub completely, due to market failure. Therefore, it is important that the EU makes available seed funding of the order of magnitude 1 -1.5 MEUR.
We are also looking for interested parties to take over our Experimentation ToolKit (ETK). The ETK allows for quantitative experiments that can be replicated at low cost. The ETK paves the way for much more data collection to understand the value of music better.
#§IMP-ACT-IA§#
I#§PRO-GRE-PG§# #@FOL-UP-FU@#
Follow-up of recommendations and comments from previous review(s)
All recommendations regarding the deliverables have been implemented, and the affected deliverables have been resubmitted.

We discuss the recommendations of the reviewers below:
- Strengthen the theoretical framework regarding value by discussing the ethical underpinnings and relevance of the project ambition.
  - Deliverable D1.2 has a new section, considering the ethical value of music.
- Ensure that all project material (e.g., posters) includes a reference to EU funding.
  - We have updated the relevant materials.
- Ensure commitment to Open Access for publications, for example, by targeting Open Access journals specifically as part of the dissemination and communication strategy.
  - Open Access is prioritized by the participating universities. This recommendation, therefore, aligns perfectly with the policies of both universities. Publications will be made available via the open-access repositories of VU and UPV. This is explicitly stated in the revised version of the data management plan.
- The project would benefit from continuous monitoring and advice throughout from the Ethics Board to mitigate any risks related to handling sensitive data and potentially vulnerable subjects, especially in connection with the Spanish Living Lab in the hospital.
  - We have installed an external ethics board. Additionally, we closely work with the Ethics boards of both universities. Specifically for the healthcare experiment, there is close interaction with the ethics board of the hospital.
- Ensure that all recommendations of the Ethics Board Report 2 (D9.6) are implemented, particularly in V2 of the Data Management Plan as specified.
  - We have explained in more detail what fingerprinting is.
  - We have detailed which data is stored by whom and where.
  - Note that the role of CMOs is to store large data sets for their business processes already. We follow the internal procedures of the CMOs.
  - The exchange of data between CMOs is mostly part of their current business. For data transfers not part of this agreement, specific contracts have been created/
- Consider what mechanisms and agreements the consortium will use to commercialise and share any revenues generated by project outputs
  - Products that can be commercialized are, in most cases, tied to the partners that created the products. This specifically holds for the Music360 frontend (BMAT) and the Ecosphere tooling (TVE). Commercialization of these products requires arrangements with the respective companies.
  - We consider the transfer of the platform to SCAPR/CISAC as the most viable option. This can be done in various ways, ranging from simply selling the software to offering it as a service. How this is concretely done is up to SCAPR/CISAC.

#§FOL-UP-FU§# #@IMP-ACT-IA@#
## 3. Exploitation primarily in non-associated third countries
n.a.
#§IMP-ACT-IA§# #@CON-MET-CM@#
## 4. Open science
Our open science policy is already explained in the project proposal.
#§CON-MET-CM§# #@WRK-PLA-WP@#
## 5. Deviations from Annex 1 and Annex 2
## 5.1 Tasks/objectives
1. Objective 2: Standardized, trusted, and unified collection and representation of music metadata.
Deviation:
Implementation of a full secure multi-party computing (SMPC) framework was not feasible.
Justification:
- SMPC technologies are too immature for production-level inclusion in a standardized approach
- It was never the goal of the project to develop SMPC technology itself. Rather, the aim was to use them
Mitigation:
- We developed several use cases of SMPC technology:
  - Calculation of average revenue of performers, without exposing their individual data, with Prio+
  - Design of a solution to keep the harvested relationship between the IPI (authors) and IPN (performers) secret, while still using the relationship in queries
- We developed an approach to select relevant SMPC techniques to satisfy a complex set of security requirements, to be used by non-SMPC experts.
Impact:
- Partial achievement did not affect overall project objectives
- Core methodology and key results were successfully validated

2. Objective 4: Ecosystem-level reporting and analysis of music value creation, distribution and consumption
Deviation:
A fully automated connection between the Ecosphere toolset and the Music360 dataset was not possible.
Justification:
- Data as provided by the Music360 dataset and as needed by the Ecosphere ecosystem analysis were semantically too different to allow for automated inclusion in the analysis
- Data as provided by the Music360 dataset is too domain-specific and too case-specific to allow for automated inclusion in the analysis
Mitigation:
We developed an example, the RAAP/PPI case, to show how data can be extracted from the Music360 dataset, and transform it in such a way, that it can be included in the Ecosphere ecosystem analysis tooling
Impact:
- Partial achievement did not affect overall project objectives
- Ecosystem methodology and associated tooling were successfully validated

3. Change of Communication Channels and Strategy
Deviation:
Communication channels did not always behave as expected, and some metrics were less relevant
Justification:
- Initial communication strategy was not fully aligned with evolving digital communication practices
- Rapid changes in how younger audiences (Gen Z) consume content required adaptation
- Shift towards more effective platforms was agreed with the European Commission during the first review
Mitigation:
Adaption of strategy after review 1
Impact:
- Improved reach and engagement with relevant stakeholders
- Increased visibility within industry networks
- Strengthened overall dissemination effectiveness

Living Labs Implementation
Deviation:
Spain (Hospital Use Case): Significant delays due to administrative and operational constraints
Justification:
- Healthcare environments require additional approvals and coordination processes
- Natural disaster in Spain. External factors beyond consortium control influenced implementation timeline
- Planned experimentation partner could not execute the experiment
Mitigation:
- Delayed the experiment
- Found another hospital as experimentation partner
Impact:
- No impact on overall project conclusions
- Insights from other Living Labs compensated for delays
- Validity of methodology and results maintained.

### 5.2 Use of resources
Include explanations on deviations of the use of resources between actual and planned use of resources in Annex 1, especially related to person-months per work package.
Include explanations on transfer of costs categories (if applicable).
Include explanations on adjustments to previous financial statements (if applicable).
#### 5.2.1 Unforeseen subcontracting
n.a.
#### 5.2.2 Unforeseen use of in kind contributions
n.a.
#§WRK-PLA-WP§#

HISTORY OF CHANGES
VERSION	PUBLICATION DATE	CHANGE
1.0	15.12.2021	Initial version (new MFF).
1.1	01.05.2023	Minor updates in Part A. / Added section 1.4 on updates to the plan for exploitation and dissemination of results.