## Deliverables
Deliverables for Project
Deliverables
Work Package No | Deliverable Related No | Deliverable No | Deliverable Name | Description | Lead Beneficiary | Type | Dissemination Level | Due Date | New Due Date (if delay) | Delivery Date | Approval Date | Status
WP1 | D1.1 | D1 | A framework to quantify and qualify the value of music – version 1 | Defines a conceptual framework to measure the monetary and non-monetary value of music in a quantitative and qualitative way, firmly founded in economic and social theory. The framework will be multi-stakeholder, meaning that it will define the value of music for various stakeholders such as creative entities, music user, and policy makers. Also included are methods and techniques to measure the various rubrics. | UPV | R | PU | 31 Dec 2023 | 31 Jan 2024 | 29 Jan 2024 | 10 Jul 2024 | Approved
WP1 | D1.2 | D2 | A framework to quantify and qualify the value of music – version 2 | A revised version of the framework, including the lessons learned from testing the framework in the Living Labs. | UPV | R | PU | 31 Oct 2024 |  | 30 Oct 2024 |  | Submitted
WP2 | D2.1 | D3 | An ontology of the value of music – version 1 | An ontology of the value of music – version 1. This a machine processable version of the conceptualization in D1.1. | UPV | R | PU | 31 Oct 2023 |  | 30 Oct 2023 | 10 Jul 2024 | Approved
WP2 | D2.2 | D4 | A distributed architecture and implementation for music data collection, representation, and distribution – version 1 | First version of a system to store and obtain data concerning the value of music in a distributed way, e.g. without using centralized information sources. Challenge is to include information sources from IPR societies, additional information collected by BMAT, and information from customer surveys. | UPV | OTHER | PU | 31 Dec 2023 | 19 Jul 2024 | 23 Jul 2024 | 13 Sep 2024 | Approved
WP2 | D2.3 | D5 | Secure and trusted sharing of music data– version 1 | First version of a security architecture. The focus will be on authorization and access control of information stored at various sources. | STICHTING VU | OTHER | PU | 29 Feb 2024 | 30 Apr 2024 | 21 Apr 2024 | 10 Jul 2024 | Approved
WP2 | D2.4 | D6 | An ontology of the value of music – version 2 | Improved of the machine processable ontology by using living lab results. | UPV | OTHER | PU | 31 Jan 2025 | 31 Mar 2025 | 03 Apr 2025 |  | Submitted
WP2 | D2.5 | D7 | A distributed architecture and implementation for music data collection, representation, and distribution –version 2 | A revised and improved information architecure, based on the living lab results. | UPV | OTHER | PU | 31 Mar 2025 | 31 May 2025 | 03 Jun 2025 |  | Submitted
WP2 | D2.6 | D8 | Secure and trusted sharing of music data– version 2 | Second version of a security architecture. In the use case that we foresee, there is a need to use the collected data for calculations, e.g. to provide aggregated figures and ecosystem analysis. For this, the information needs to be used by others than the owners, without disclosing it. | STICHTING VU | OTHER | PU | 30 Apr 2025 | 30 Jun 2025 | 30 Jun 2025 |  | Submitted
WP3 | D3.1 | D9 | Reusable dashboard to present and analyze the value of music - version 1 | Web frontend for stakeholder-oriented modelling and value analysis. The web frontend will use the collected data, and presents it in various ways, e.g. depending on the different kinds of stakeholders. | BMAT | OTHER | PU | 31 May 2024 | 02 Sep 2024 | 02 Sep 2024 |  | Submitted
WP3 | D3.2 | D10 | Reusable dashboards to present and analyze the value of music – version 2 | A revisited version of the dashboard, including the lessons learned by the Living Labs. | BMAT | OTHER | PU | 30 Sep 2025 | 31 Dec 2025 | 08 Jan 2026 |  | Submitted
WP4 | D4.1 | D11 | Dashboard for ecosystem modelling – version 1 | Software tooling to model music ecosystems including valuation assessment on the ecosystem level. The focus will be on graphical modelling of monetary and non-monetary value flows in an ecosystem. | TVE | OTHER | SEN | 31 May 2024 |  | 01 Jun 2024 |  | Submitted
WP4 | D4.2 | D12 | Dashboard for ecosystem level value analysis -version 2 | Software tooling to model music ecosystems including valuation assessment on the ecosystem level. The focus will be on inclusion of data feeds on the value of music. | TVE | OTHER | SEN | 31 Aug 2025 | 30 Nov 2025 | 08 Dec 2025 |  | Submitted
WP5 | D5.1 | D13 | Sustainable business model of Music360 dashboard – version 1 | A sustainable ecosystem business model of the Dashboard and data collection mechanisms of the participating countries, tested in simulations. | Sena | R | PU | 30 Jun 2024 |  | 02 Jul 2024 |  | Submitted
WP5 | D5.2 | D14 | Sustainable business model of Music360 dashboard – version 2 | A revised and scalable, validated business model for the Dashboard, based on experiences and interviews in WP6. | Sena | R | PU | 31 Oct 2025 |  | 10 Nov 2025 |  | Submitted
WP6 | D6.1 | D15 | Stakeholder needs for understanding the value of music – version 1 | This deliverable comprises the requirements of stakeholder needs with respect to understanding of the value of music. Focus is on the national living labs. | IMRO | R | PU | 30 Apr 2023 |  | 02 May 2023 | 10 Jul 2024 | Approved
WP6 | D6.2 | D16 | Stakeholder needs for understanding the value of music – version 2 | This deliverable comprises the requirements of stakeholder needs with respect to understanding of the value of music. Focus is on the international living lab. | GDA | R | PU | 31 Aug 2024 | 30 Oct 2024 | 30 Oct 2024 |  | Submitted
WP6 | D6.3 | D17 | National music ecosystem models | Understanding and analysis of the national ecosystems in WP 6 by means of e3value ecosystem models. | TVE | R | PU | 30 Sep 2023 |  | 21 Apr 2024 | 10 Jul 2024 | Approved
WP6 | D6.4 | D18 | International music ecosystem models | Understanding and analysis of the international ecosystem in WP6 by means of e3value ecosystem models. | TVE | R | PU | 28 Feb 2025 | 07 Apr 2025 | 29 Apr 2025 |  | Submitted
WP6 | D6.5 | D19 | National living labs | Implementation of the dashboards and associated data collection mechanisms for the national living labs and use cases, and validation in national contexts. | GDA | DEM | SEN | 30 Jun 2024 | 06 Oct 2024 | 04 Oct 2024 |  | Submitted
WP6 | D6.6 | D20 | International living lab | Implementation of the dashboards and associated data collection mechanisms, and validation in an international context. | IMRO | DEM | SEN | 28 Feb 2026 |  | 05 Mar 2026 |  | Submitted
WP6 | D6.7 | D21 | Open data access living labs | Public, and published, API-controlled access to data found in the living labs. | BMAT | DATA | PU | 28 Feb 2026 |  | 30 Mar 2026 |  | Submitted
WP7 | D7.1 | D22 | Dissemination,communication, and exploitation plan version 1 | This deliverable comprises a comprehensive dissemination plan (e.g. at the various music industry events and outlets, and academia), a communication plan (e.g. regarding the press, social media), and an exploitation plan. | STICHTING VU | R | PU | 31 Aug 2023 | 19 Jul 2024 | 23 Jul 2024 | 13 Sep 2024 | Approved
WP7 | D7.2 | D23 | Dissemination,communication and exploitation plan version 2 | This deliverable is a revised versiion of the first dissemination, communication, and exploitation plan. | STICHTING VU | R | PU | 31 Aug 2024 |  | 31 Aug 2024 |  | Submitted
WP7 | D7.3 | D24 | Intermediate Policy Brief | We will develop a policy brief for EU- and national governments to present and discuss the impact, and required changes regarding policy related issues. | Buma | R | PU | 31 May 2024 |  | 01 Jun 2024 |  | Submitted
WP7 | D7.4 | D25 | Final Policy Brief | This deliverable is a revised version of the first policy brief. | Sena | R | PU | 28 Feb 2026 |  |  |  | Pending
WP7 | D7.5 | D27 | Final report on communication, dissemination, and exploitation | TBD | STICHTING VU | R | PU | 30 Apr 2025 | 28 Feb 2026 |  |  | Pending
WP7 | D7.6 | D26 | Dissemination, communication and exploitation plan version 3 | Update of the dissemination, communication and exploitation plan. | STICHTING VU | R | PU | 31 Dec 2025 | 31 Jan 2026 | 02 Feb 2026 |  | Submitted
WP8 | D8.1 | D28 | Management handbook | This deliverable is a compact expression of the procedures, such as quality control, used by the project. Its goal is to ensure smooth and high quality project execution. | STICHTING VU | R | SEN | 31 May 2023 | 19 Jul 2024 | 23 Jul 2024 | 29 Aug 2024 | Approved
WP8 | D8.2 | D29 | Data management plan version 1 | This is the Data Management plan | STICHTING VU | DMP | SEN | 31 Aug 2023 |  | 15 Sep 2023 |  | Submitted
WP8 | D8.3 | D37 | Data management plan version 2 | This is the updated data management plan. | STICHTING VU | DMP | SEN | 31 Aug 2024 |  | 31 Aug 2024 |  | Submitted
WP8 | D8.4 | D38 | Data management plan final | Final version of the data management plan | STICHTING VU | DMP | SEN | 28 Feb 2026 |  | 28 Feb 2026 |  | Submitted
WP9 | D9.1 | D30 | H - Requirement No. 1 | Participants - The procedures and criteria that will be used to identify/recruit research participants must be submitted as a deliverable before the start of the relevant activities. The informed consent procedures that will be implemented for the research participants must be clarified and submitted as a deliverable before the start of the relevant activities. Templates of the informed consent/assent forms and information sheets (in language and terms intelligible to the participants) must be submitted as a deliverable before the start of the relevant activities. For children and/or adults unable to give informed consent involved, details on how the consent of the legal representatives (and assent of the research participant, when applicable) will be obtained must be submitted as a deliverable before the start of the relevant activities. Since vulnerable individuals/groups will be involved, adequate measures to protect them, prevent coercion and undue inducement, exacerbation of their vulnerability, and minimise the risk of harm and/or stigmatisation must be submitted as a deliverable before the start of the relevant activities. Detailed information on the incidental/unexpected findings policy (including the disclosure policy in case of unexpected findings) must be submitted as a deliverable before the start of the relevant activities. Copies of opinions/approvals by ethics committees and/or competent authorities for the research with humans must be obtained before the start of the relevant activities, and submitted as a deliverable before the start of the relevant activities. | STICHTING VU | ETHICS | SEN | 30 Apr 2023 |  | 02 May 2023 |  | Submitted
WP9 | D9.2 | D31 | POPD - Requirement No. 3 | Personal data deliverable - Clarification how all of the personal data that will be processed are relevant and limited to the purposes of the research project (in accordance with the ‘data minimisation ‘principle) participants must be submitted as a deliverable before the start of the relevant activities. A description of the technical and organisational measures that will be implemented to safeguard the rights and freedoms of the data subjects/research participants must be submitted as a deliverable before the start of the relevant activities. A description of the security measures that will be implemented to prevent unauthorised access to personal data or the equipment used for processing must be submitted as a deliverable before the start of the relevant activities. Description of the anonymisation/pseudonymisation techniques that will be implemented must be submitted as a deliverable before the start of the relevant activities. Templates of the informed consent forms and information sheets with regard to data processing (in language and terms intelligible to the participants, including DPO contact details for host institutions required to appoint a DPO under the General Data Protection Regulation 2016/679) must be submitted as a deliverable before the start of the relevant activities. For the further processing of previously collected personal data, an explicit confirmation that the beneficiary has lawful basis for the data processing and that the appropriate technical and organisational measures are in place to safeguard the rights of the data subjects must be submitted as a deliverable before the start of the relevant activities. | STICHTING VU | ETHICS | SEN | 30 Apr 2023 |  | 02 May 2023 |  | Submitted
WP9 | D9.3 | D32 | AI - Requirement No. 4 | Ethics Handbook deliverable - The Ethics Handbook is developed and submitted as a stand-alone deliverable, under the supervision of the Ethics Board. This deliverable must include: - a detailed explanation on the measures taken to prevent, avoid and mitigate potential bias, discrimination and stigmatisation in input data and algorithm design and outcomes - detailed explanation on how the research participants and/or end-users will be informed about: (1) their interaction with an AI system/technology (if relevant); (2) the abilities, limitations, risks and benefits of the AI system/technique; (3) the manner in which decisions are taken and the logic behind them (if relevant) must be submitted as part of the Ethics Handbook deliverable. - an assessment/evaluation report of the ethics risks related to the AI. - a risk mitigation plan with a description of the measures set in place to prevent/mitigate any potential negative personal/social/environmental impacts during the research, deployment and post-deployment phase. | STICHTING VU | ETHICS | SEN | 30 Apr 2023 |  | 02 May 2023 |  | Submitted
WP9 | D9.4 | D33 | OEI - Requirement No. 5 | Creation of the project Ethics Board - The complexity and seriousness of the raised ethics issues require independent supervision and monitoring from the start of the project (M1) by an external Ethics Board comprising appropriate expertise in research ethics specialising in handling of human involvement, medical ethics, AI ethics, and personal data protection. Reports by the Ethics Board are due in M6, M14, and M36. | STICHTING VU | ETHICS | SEN | 31 Mar 2023 | 03 May 2023 | 02 May 2023 |  | Submitted
WP9 | D9.5 | D34 | OEI - Requirement No. 6 | Ethics Board report - 1 | STICHTING VU | ETHICS | SEN | 31 Aug 2023 |  | 15 Sep 2023 |  | Submitted
WP9 | D9.6 | D35 | OEI - Requirement No. 7 | Ethics Board report - 2 | STICHTING VU | ETHICS | SEN | 31 Mar 2024 | 30 Apr 2024 | 18 Mar 2025 |  | Submitted
WP9 | D9.7 | D36 | OEI - Requirement No. 8 | Ethics Board report - final | STICHTING VU | ETHICS | SEN | 28 Feb 2026 |  | 28 Feb 2026 |  | Submitted