Music360 – Communication/Dissemination Meeting

Date: Tuesday 16 January 2024, 14.00h
Present: Denis, Lisa, Piia, Fransisco, Frank, Ralph, Lima, Mekky

- Music360-website (Goal: 25.000 visitors/year) -  demonstration by Denis

  - Actions

    - Add more images of music and enjoying music

    - Add more detailed information explaining the deliverables

    - Start writing blog and news articles (Mekky will share an outlook invite with reminder for the blog of the month)

    - The schedule of content delivery can be found on the Drive

    - Mekky and Lima will work on standardized project logo and description that can be posted on project parnters’s website

    - For reference, example of project website: Grade2XL

- Music360-PR Material for events: Lima explains that based on her experience in other project, we would like to have flyers, a project poster (including the donor, partners, logo, etc.), and a banner

  - Actions

    - Fransisco will discuss internally with the graphic designer if this is something he can help with, if so, he will share examples of his work

    - If not, Mekky will ask Ralph if somebody from SENA could help with the graphic design

- AOB

  - Frank (BUMA) will go to Noorderslag festival on Friday 19/01 and use this opportunity for Music360 dissemination. He will write a short news article afterwards, and take pictures that can be used on the Music360-social media channels

  - Mekky will share again the link to Drive where a picture and short bio can be added for your introduction as partner in the Music360-project: see link

- Next meeting:

  - Tuesday 31 January 14.00-15.00h  (In Ireland: 13.00-14.00h)